## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | J.W 3/03/2019 | Pass | J.W 4/01/2019
(Rules Story)As a Player I want to know the rules of the game so that I can play the game more effectively. | **Given** I am in a game **when** it is my turn **then** I want my turn to be comprised of different states that makes each round more fluid. |  |  | Pass | J.W 4/03/2019
| **Given** that I am in a game **when** it is my turn **then** I want to know that it is my turn and be able to perform my turn actions. |  |  | Pass | J.W 4/03/2019
| **Given** that I am in a game **when** it is not my turn **then** I want to wait for my opponent to finish their turn. |  |  | Pass | J.W 4/03/2019
| **Given** that I am in a game **when** the game is ending **then** I want to be able to view the final state of the board and exit the game. |  |  | Pass | J.W 4/03/2019
| **Given** that it is my turn **when** I move a piece **then** I want to know that my move is being validated in accordance with American Tournament Rules. |  |  | Pass | J.W 4/03/2019
| **Given** that I made a valid move **when** I want to redo my move **then** I want the ability to redo the move taken in lieu of a superior move. |  |  | Pass | J.W 4/03/2019
| **Given** that I made a valid move **when** I go to end my turn **then** I want the enemy player and the server to know that I have made my move. |  |  | Pass | J.W 4/03/2019
| **Given** the opponent has finished moving **when** I start my turn **then** I want my game to refresh to display the new results. |  |  | Pass | J.W 4/03/2019
| **Given** I am currently not in the middle of a move **when** I want to give up **then** a state becomes available that allows me to give up. |  |  | Pass | J.W 4/03/2019
| **Given** I am playing a game **when** I go to submit a move **then** I want my move to accurately be sent to the game. |  |  | Pass | J.W 4/03/2019
| **Given** my turn has ended **when** I am waiting for my turn **then** I want the server to constantly check to see if its my turn yet. |  |  | Pass | J.W 4/03/2019
| **Given** the game is over **when** I am looking for the reason **then** I want to be able to know exactly why. |  |  | Pass | J.W 4/03/2019
(movement)As a Player I want to be able to move my piece according to the rules so that I can anticipate my own movement as well as the opponent. | **Given** it is my turn **when** I am playing a game of checkers **then** I want to be able to move on my turn. |  |  | Pass | J.W 4/03/2019
| **Given** it is not my turn **when** I try to move a piece **then** I expect it to not move. |  |  | Pass | J.W 4/03/2019
| **Given** it is my turn **when** I move a piece to a white space **then** I expect the game to not allow the player to drop their piece. |  |  | Pass | J.W 4/03/2019
| **Given** it is my turn **when** I move a piece either perpendicularly or horizontally **then** I expect the game to not allow the player to drop their piece. |  |  | Pass | J.W 4/03/2019
| **Given** it is my turn and the piece is not a king **when** I reach the other end of the board **then** I expect the piece to become a king. |  |  | Pass | J.W 4/03/2019
| **Given** a jump is available **when** I take the turn **then** I am required to make that jump (with a choice if multiple jumps are available). |  |  | Fail | J.W 4/03/2019 can't not take the turn, and
| **Given** it is my turn and the piece is a king **when** I move that piece **then** I want to the option of moving the king forwards or backwards. |  |  | Pass | J.W 4/03/2019
| **Given** that I can jump another piece **when** I land my prior jump **then** I can continue jumping. |  |  | Pass | J.W 4/03/2019
| **Given** I have shown poor judgement **when** I have made a move **then** I can undo that move and start that move over again. |  |  | Pass | J.W 4/03/2019
| **Given** it is my turn **when** I move a piece over an enemy piece **then** that piece is removed from the game. |  |  | Pass | J.W 4/03/2019
(board stories)As a Player I want to be able to see a Checkers game board with all the pieces on it so that I can start a game against my opponent. | **Given** that I am logged into the WebCheckers app, **when** I start a game with an opponent, **then** I want to see a Checkers board with spaces and pieces characterized by their respective colors. |  |  | Pass | J.W 4/03/2019
| **Given** that I start a game with an opponent **when** the board is displayed to my screen **then** I expect the board's orientation to be such that my pieces are on the bottom. |  |  | Pass | J.W 4/03/2019
| **Given** a board has been created **when** I call upon an element within the board **then** the board element is exactly what I expect it to be. |  |  | Pass | J.W 4/03/2019
| **Given** that I have started a game against my opponent, **when** I take my turn, **then** I expect the board should be updated according to the move I made. |  |  | Pass | J.W 4/03/2019
| **Given** that a board has been created **when** I make modifications to the current game state **then** only the board I made modifications to will display these changes. |  |  | Pass | J.W 4/03/2019
| **Given** that I am playing a game against my opponent, **when** my opponent takes a turn, **then** I should be able to tell which piece he moved and where he moved it. |  |  | Pass | J.W 4/03/2019
| **Given** that I am a player in a game **when** I reach a boundary with a piece **then** I cannot move my piece beyond that boundary. |  |  | Pass | J.W 4/03/2019
| **Given** that I am a player **when** I start a game **then** I will get the same exact board layout every time. |  |  | Pass | J.W 4/03/2019
| **Given** that i am playing a game against my opponent, **when** there are no more valid moves that a player can make, **then** the game will over. |  |  | Pass | J.W 4/03/2019
| **Given** that I am playing a game **when** I take all my enemies' pieces **then** the game will end and I will be victorious. |  |  | Pass | J.W 4/03/2019
(piece story) As a Player I want a recognizable player piece so that I’m not thrown off by the design of the pieces in my game. | **Given** that there is an existing piece **when** I click on a piece **then** I expect either to be able to pick it up or be informed that it is not my piece. |  |  | Pass | J.W 4/03/2019
| **Given** that I start a game **when** the checkers board loads **then** I expect my pieces to display some indication which player they belong to. |  |  | Pass | J.W 4/03/2019
| **Given** it is my turn **when** successfully Jump an opponent **then** I expect to decimate the opponent's piece. |  |  | Fail | J.W 4/03/2019
| **Given** that I reach the other end of the board **when** my piece has become a king **then** I want to be able to be able to distinguish the king from single pieces. |  |  | Pass | J.W 4/03/2019
| **Given** that a piece is King and it is my turn **when** I am deciding my moves **then** I want to that piece to have special abilities befitting a King. |  |  | Pass | J.W 4/03/2019
As a Player I want to see my piece fit perfectly on a well-designed square so that I can easily see my next move. | **Given** that there is a space **when** I drop a piece in a space then I **expect** the piece to fit neatly in the space. |  |  | Pass | J.W 4/03/2019
| **Given** that a space exists **when** I look for an individual space **then** I expect to find it. |  |  | Pass | J.W 4/03/2019
| **Given** that a space exists **when** I look at the game board **then** I can determine whether a piece is on that space. |  |  | Pass | J.W 4/03/2019
| **Given** that a space exists **when** I look at the game board **then** I can determine whether a space is valid or not by color. |  |  | Pass | J.W 4/03/2019
| **Given** that I am playing a game **when** I click a space **then** I expect to see the result of my action. |  |  | Pass | J.W 4/03/2019